## Slide 1: Project Management, Part 2
Corresponding to Chapter 2 of “Systems analysis and design”, 6th edition, by Dennis, wixom, and roth

## Slide 2: Learning Objectives
Understand additional project estimation practices (now that a work plan is developed or in progress)
Understand scope creep and best practices for dealing with it
Describe basic concepts of risk management
Describe project staffing issues, including motivation and effective group collaboration tools and techniques

## Slide 3: Project Management: Recap
Notes: We talked about the Work Breakdown Structure and the Project Work Plan, which have to do with both project size (number of tasks) and time. I mentioned Microsoft Project and other project management software as a tool to create a project work plan. These softwares can also be used to manage the cost aspect.

## Slide 4: Project Estimates Require Refinement
  Even projects with high-quality estimates will need refinement throughout the life of the project

## Slide 5: Timeboxing
Time estimating techniques may reveal that the project requires more time than we have available
Timeboxing helps in these situations
      Set a tight but realistic deadline. Identify core, essential functional requirements
      Team limits its focus just to essential functions
      High quality is stressed
      Other functions will be added later
      Repeat to add refinements and enhancements

## Slide 6: When a Target Date is Missed…
Don’t assume you can catch up
The ONLY situation in which you can make up time is when:
      The remainder of the project is simpler than the part you fell behind on, and
      The remainder of the project is simpler than you expected when the original estimates were made.
Evaluate the complexity of the remainder of the project to determine the correct schedule adjustment.
Adding people is not always the right way to handle schedule slippages.
Notes: If the rest of the project is simpler than the part that was late and is no more complex
than the original estimate assumed, you can’t make up lost time, but you can shift the
entire schedule back by the amount of time you are behind. E.g., shift the entire schedule
back three weeks if you are behind three weeks now. Requires moving the target date.
IF the rest of the project is as complex as the part that was late, you should adjust
estimates for all scheduled dates by the percentage your estimate was off for the current
phase. E.g., if you are three weeks late on a 12-week phase (25%), increase all remaining
deadlines by 25%.
Ask: Why is adding people not always the right way? (training time, additional coordination, etc.)

## Slide 7: Managing Scope
Beware of scope creep
Best practices:
  For projects with unclear requirements, consider extensive user meetings and/or prototypes early in the project
  Implement a formal change approval process
  Defer additional requirements as future system enhancements
Notes: In the formal change approval process, some suggestions can be approved and others denied. In all cases, the project manager and/or team of analysts lets the user know the impact the potential change would have on project time or cost

## Slide 8: Managing Risk
Remember that the project sponsor and/or the analyst completed a feasibility study before the project started.
Now, the project manager takes responsibility for managing project risks.
Risk = Probability x Potential Impact
Notes: Look at risk assessment handout

## Slide 9: Managing Risk
What are some risks associated with the semester project?
  Let’s plot them on a risk assessment matrix
Techniques for managing risk
  Avoidance
  Transfer (insure or share)
  Reduction (mitigation)
  Retention (accept)
Notes: A programmer gets upset and quits (unlikely and not major impact – green area)
Development costs go over the $35K budget (possible and moderate impact – yellow area)
No one books any conference rooms
(Probably don’t have any risks in the red area – otherwise the project would halt or would have to have major changes)
In your feasibility analysis that you will do for mid-semester deliverable, you don’t have to use a matrix (you can if you want), but you should list potential risks and how you plan to deal with them

## Slide 10: Project Management: Another major job role
Notes: The main job of the project manager is to balance time, cost, and scope. However, another major role of the project manager that cannot be ignored is staffing issues.

## Slide 11: Staffing Considerations
Match skills to project needs whenever possible
Consider technical skills and interpersonal skills
      Technical skills are not sufficient – need to be able to work with others
      Use training and outside sources (consultants, vendor support) when skills are not readily available
Staffing levels will change over a project’s lifetime
Notes: Availability is a problem with flex time and telecommuting options today. People might also be on other projects

## Slide 12: Staffing Considerations
Adding staff adds overhead; not always productive
Establish a reporting structure; for teams with no formal leader, establish an informal team lead
Team sizes should be less than 8-10; otherwise create sub-teams
Notes: Ask students: why do you think adding staff is not always productive?
I encourage you to determine a team lead for your semester team; not necessarily a person in charge of everyone else, but someone responsible to make sure coordination and communication happens smoothly.

## Slide 13: Motivation
Use monetary rewards cautiously
Use intrinsic rewards
      Recognition
      Achievement
      The work itself
      Responsibility
      Advancement
      Chance to learn new skills
Notes: Technical people generally are not motivated by money as long as they feel they are paid a fair salary.

## Slide 14: Motivation
Consider the “de-motivators” … DO NOT
      Assign unrealistic deadlines
      Ignore good efforts
      Accept a low-quality product
      Give everyone on the project the same raise
      Make an important decision without the team’s input
      Maintain poor working conditions
Notes: Why not give everyone a raise for a good job on the team?

## Slide 15: Improving Team Performance
Make sure team understands the project and its goals
Establish operating procedures up front (Project Charter)
      Availability: When can you meet or complete work?
      Status reporting: What are the individual deadlines?
      Meetings: How often? What days? In person or online?
      Documentation storage: Where do we store our files?
Provide formal or informal standards
Establish methods for conflict resolution
Notes: Established standards can be communicated informally or they can be documented formally (esp for larger or complex projects or where the project manager foresees potential conflict). Usually it is done informally; for the class I’m going to have you create a written project charter, basically so I can force you to establish group team procedures.
Example from semester where group did not coordinate well because they were using different means of communication
For a list of standards, see Figure 2-18 (p 60 in 6th edition; p 73 in 5th edition). Standards can be included in the operating procedures, or they might be separate

## Slide 16: Working on a Team (From a team member perspective)
Key aspects of working on a team (3 C’s)
      Communication: Expectations and team cohesion
      Conveyance: Sharing task information and work
      Convergence: Making decisions about the work
Face-to-face or distributed (or combination)
      Both types face issues related to the 3 C’s
      Distributed teams are more prone to these issues but can be just as effective
Notes: The info on the previous slide fits with the textbook material on managing group projects. I’d like to provide a few more tools and practices that might help you based on my own experience in industry, in my time as a student, and in my current work.
How many of you have had a bad experience working in a team on a school project?
At my first IT job, all teamwork I did was face-to-face or within the same office. When I did consulting I did some face-to-face work and also did some virtual work with out-of-state clients. Now as a professor I am constantly working on projects with people from around the world, using more collaboration technology.

## Slide 17: Common Team Issues (and ways to address them)
Communication issues
      Misunderstandings about expectations
      Freeriding
      Missed communication
Processes to help
      Meet face-to-face (or through video) at beginning of project
      Set expectations up front about who does what
      Establish multiple ways to get in touch
      Be professional: Address concerns openly, and respond to teammates within a reasonable amount of time
Technologies
      Skype/Hangouts; email; phone; text or equivalent; forums
Notes: Both processes and technologies can help in addressing these issues.
Technologies listed in order from most effective to least effective (generally speaking), but people who are comfortable with text can make it work
(Give example of team who didn’t receive texts)
Each of the technologies can be used for one-on-one, but can also be used for whole groups; video chat is preferable for first meeting for those who never meet face-to-face
GoToMeeting and Webex are also commonly used in industry

## Slide 18: Common Team Issues (and ways to address them)
Conveyance issues
      Duplicate work
      Conflicting changes
      Unable to see others’ work
Processes to help
      Use shared document storage (preferred)
      OR be clear about who is working on the “master copy”
      Set expectations up front about access to information and work
Technologies
      Dropbox/Box/shared_drives; Google Docs/Drive; email
Notes: Dropbox is also nice when you install the app on your computer/laptop/smartphone because the files are always up to date on your own device.

## Slide 19: Common Team Issues (and ways to address them)
Convergence issues
      Groupthink
      Disagreement
      Lack of input from some team members
Processes to help
      Do individual brainstorming first, then come together
      Spend time in initial meeting establishing rapport
      Anonymous voting
      Do not make important group decisions over email/text – meet together
Technologies
      Skype/Hangouts; Google Docs/Drive with chat;
Notes: Recap: It’s important to establish these norms ahead of time. A little extra effort up front saves a lot of time and stress later on.

## Slide 20: Two Team Strategies
Work synchronously
      Meet in person / Google Docs / Skype with screen sharing
      Benefits: Concurrent feedback, creativity, full input
      Drawbacks: Scheduling, lost efficiency
Divide and conquer
      Meet to decide how work with be divided; then work individually; then combine; then every member reviews and approves combined work
      Benefits: Efficient, scheduling, use key strengths of individuals
      Drawbacks: Feedback, decision making
Notes: Give examples from my research projects on how I often use divide and conquer
Decide on a strategy or use a combination based on the type of work and how the benefits and drawbacks would contribute – for example, with work that is fuzzy use synchronous; for work that is clear, use divide and conquer

## Slide 21: Recap on collaboration technologies
Highly recommend learning to use:
  Skype/Hangouts/GoToMeeting/AdobeConnect/etc.
  Google Docs / Drive
  Dropbox (for individual work, too)
    http://www.fullerton.edu/ittraining/other/dropbox/tutorial_student/
Other tools out there that aim to facilitate all aspects of team collaboration
  E.g., https://slack.com/is

## Slide 22: Learning Objectives
Understand additional project estimation practices (now that a work plan is developed or in progress)
Understand scope creep and best practices for dealing with it
Describe basic concepts of risk management
Describe project staffing issues, including motivation and effective group collaboration tools and techniques

## Slide 23: End of Slides
Start on Chapter 3 slides if there is extra time, since next week will be busy
Assignment: Meet with your team and create a team charter
(instructions on TITANium)